## Dashboard
The countdown, the checklist, the boxes, the money and who still needs your new address.
Moving day | 2026-10-24
New home | Maple Road
Budget | 1800
Countdown | Tasks done | Late tasks | Boxes packed | Told new address | Budget left
Next up |  |  | Date | Who | Status | Boxes by room | Boxes | Packed | Fragile | Arrived
Money | Planned | Paid | Still to pay |  |  | Open first | Box | To
Movers
Van and fuel
Packing
Cleaning
Storage
Deposits
Utilities
Furniture
Travel
Other
Total

## Tasks
Tasks
The checklist, counted back from moving day. Change the days before and the dates follow. 0 is moving day, and a minus number is after it.
Task | Days before | Date | Who | Done | Status | Notes
Set a budget and the moving date | 56 |  | Both | x
Get three quotes from movers | 56 |  | Sam | x
Book the movers | 49 |  | Sam | x
Start clearing out, room by room | 49 |  | Both | x
Order boxes, tape and bubble wrap | 42 |  | Alex | x
Book the day off work | 42 |  | Both | x
Sell or give away what does not come | 35 |  | Alex
Measure the new home for the furniture | 35 |  | Sam | x
Give notice on the old flat | 30 |  | Sam | x
Pack the rooms you rarely use | 28 |  | Both | x
Set up mail forwarding | 21 |  | Alex | x
Book internet at the new home | 21 |  | Sam
Tell the bank, work and the doctor | 14 |  | Both
Book cleaning for the old flat | 14 |  | Alex
Confirm the movers and the time | 10 |  | Sam
Arrange parking for the van | 10 |  | Sam
Use up the frozen food | 7 |  | Both
Pack all but the essentials | 7 |  | Both
Pack the open-first boxes | 3 |  | Alex
Defrost the fridge | 2 |  | Alex
Take photos of the old flat | 1 |  | Sam
Take the meter readings | 0 |  | Sam
Check every room and cupboard | 0 |  | Both
Hand over the keys | 0 |  | Sam
Unpack the open-first boxes | -1 |  | Both
Register with a new doctor | -7 |  | Alex
Get the deposit back | -14 |  | Sam
Unpack the last boxes | -21 |  | Both
Formulas:
Status = IF([Task]="","",IF([Done]<>"","Done",IF([Date]="","",IF([Date]<TODAY(),"Late",IF([Date]-TODAY()<=7,"This week","Coming")))))

## Boxes
Boxes
Write the number on the box and one line here: the room it leaves, the room it goes to and what is inside. Put an x as it is packed and when it arrives.
Box | From | To | What is inside | Size | Fragile | Open first | Packed | Arrived | Status | Notes
1 | Kitchen | Kitchen | Plates and bowls | Medium | x
2 | Kitchen | Kitchen | Glasses | Small | x
3 | Kitchen | Kitchen | Pots and pans | Large
4 | Kitchen | Kitchen | Baking things | Medium |  |  | x
5 | Kitchen | Kitchen | Mugs and the kettle | Small | x | x
6 | Kitchen | Kitchen | Cutlery and knives | Small
7 | Kitchen | Kitchen | Food cupboard | Medium
8 | Kitchen | Kitchen | Small appliances | Large
9 | Kitchen | Kitchen | Tea towels and aprons | Small
10 | Living room | Living room | Books A to M | Small |  |  | x
11 | Living room | Living room | Books N to Z | Small |  |  | x
12 | Living room | Living room | Lamps | Medium | x |  | x
13 | Living room | Living room | Cushions and throws | Large |  |  | x
14 | Living room | Living room | Board games | Medium |  |  | x
15 | Living room | Living room | Photo frames | Small | x |  | x
16 | Living room | Living room | Speakers and cables | Medium | x
17 | Bedroom | Bedroom | Bedding | Large |  | x
18 | Bedroom | Bedroom | Winter clothes | Large |  |  | x
19 | Bedroom | Bedroom | Shoes | Medium
20 | Bedroom | Bedroom | Summer clothes | Large |  |  | x
21 | Bedroom | Bedroom | Jewellery box and watch | Small | x
22 | Bedroom | Bedroom | Towels | Medium
23 | Kids room | Kids room | Toys | Large
24 | Kids room | Kids room | Kids books | Small
25 | Kids room | Kids room | Kids clothes | Large
26 | Kids room | Kids room | Night light and bedding | Medium |  | x
27 | Bathroom | Bathroom | Bathroom things | Small |  | x
28 | Bathroom | Bathroom | Medicine box | Small
29 | Office | Study | Files and papers | Small |  |  | x
30 | Office | Study | Monitor | Large | x |  | x
31 | Office | Study | Printer | Medium | x |  | x
32 | Office | Study | Stationery | Small |  |  | x
33 | Office | Study | Cables and chargers | Small |  | x
34 | Hallway | Hall | Coats | Large
35 | Hallway | Hall | Umbrellas and bags | Medium
36 | Garage | Garage | Tools | Medium |  |  | x
37 | Garage | Garage | Garden things | Large |  |  | x
38 | Garage | Garage | Bike gear | Medium |  |  | x
39 | Garage | Garage | Christmas decorations | Large |  |  | x

## Movers
Movers
Quotes side by side. Put an x under Chosen for the one you book, and add it to Costs.
Company | Price | Free on | Packing | Insurance | Notes | Chosen
Oak Lane Removals | 1150 | 2026-10-24 | x | x | Pack the kitchen for us
City Van Movers | 890 | 2026-10-31 |  |  | Only free the week after
Blue Box Removals | 950 | 2026-10-24 |  | x | Good reviews, can store for a week | x
The cheapest price is in green. A date in orange is not moving day.

## Costs
Costs
Everything the move costs: what you booked, what you paid and when the rest is due.
Item | Category | Company or shop | Estimate | Final price | Paid | Still to pay | Pay by | Status | Notes
Removal, 2 movers and a truck | Movers | Blue Box Removals | 950 | 950 | 200 |  | 2026-10-24
Boxes, tape and bubble wrap | Packing | Box shop | 90 | 86.4 | 86.4
End of tenancy cleaning | Cleaning | Sparkle Clean | 180 | 180 | 0 |  | 2026-10-25
Mail forwarding, 6 months | Other | Post office | 35 | 34.5 | 34.5
Internet set-up | Utilities | Fibre company | 49 |  | 0 |  | 2026-10-03
Van parking permit | Van and fuel | Council | 25 |  | 0 |  | 2026-10-14
Takeaway on moving day | Other |  | 40 |  | 0
Curtains for the new bedroom | Furniture |  | 120 |  | 0
The final price counts once you know it. Until then the estimate does.
Formulas:
Status = IF([Item]="","",IF([Still to pay]<=0,"Paid",IF([Pay by]="","To pay",IF([Pay by]<TODAY(),"Late",IF([Pay by]-TODAY()<=7,"Due soon","To pay")))))

## New address
New address
Everyone who needs your new address. Put an x under Done when you have told them.
Who | Kind | How | Account or reference | Done | Notes | Meter | Old home | New home | Date
Bank | Money | Online | Current account | x |  | Electricity |  |  | 2026-10-24
Credit card | Money | App |  | x |  | Gas |  |  | 2026-10-24
Employer | Work | Email to HR |  | x |  | Water |  |  | 2026-10-24
Doctor | Health | Form at the surgery |  |  |  | Other
Dentist | Health | Phone
Car insurance | Money | Online | Policy number |  |  | Take the readings on moving day, with a photo.
Home insurance | Money | Phone | Policy number
Electricity | Home | Online | Meter reading
Gas | Home | Online | Meter reading
Water | Home | Phone
Internet | Home | Online | Booked for the new home | x
Local council | Government | Online form
Tax office | Government | Online
Driving licence | Government | Online
Mail forwarding | Post | Post office | 6 months | x
Mobile phone | Subscriptions | App |  | x
Streaming and magazines | Subscriptions | Online
Gym | Subscriptions | At the desk
School | Other | Letter |  | x
Family and friends | People | Card with the new address
Vet | Health | Phone
Online shops | Subscriptions | Each account

## Settings
Settings
The rooms of the home you are leaving, for the boxes and the Dashboard.
Rooms
Kitchen | The Dashboard counts the boxes of each room on this list.
Living room
Bedroom
Kids room
Bathroom
Office
Hallway
Garage

## Start Here
Start here
Type only in the yellow cells. Everything else is calculated.
1 | Dashboard: moving day, the new home and your budget. Settings: the rooms of the home you leave.
2 | Tasks: a checklist is ready, counted back from moving day. Put an x under Done as you go.
3 | Boxes: write a number on each box and one line here. Put an x when it is packed and when it arrives.
4 | Movers and Costs: compare the quotes, then note what you book, what you paid and when the rest is due.
5 | New address: everyone who needs it, with the meter readings to take on moving day.
The example move, its companies and its places are made up. Delete them and add your own.
Change moving day and every task date moves with it.
Works in Google Sheets and Microsoft Excel, in any currency.