## Dashboard
The countdown, the guests, the checklist and the money for the party.
Party | Mia turns 7
Date | 2026-10-24 | Starts | 14:00
Budget | 1100
Countdown | Coming | No answer yet | Tasks done | Late tasks | Budget left
Next up |  |  | Date | Who | Status | Guests | Adults | Kids | Total
Coming
Maybe
No answer yet
Can't come
Invited
Money | Planned | Paid | Still to pay |  |  | Dietary needs of guests coming | Guests
Venue | [5 empty] | Vegetarian
Cake | [5 empty] | Vegan
Decorations | [5 empty] | Gluten free
Entertainment | [5 empty] | Dairy free
Rentals | [5 empty] | Nut allergy
Invitations | [5 empty] | Halal
Favours | [5 empty] | Kosher
Photos | [5 empty] | Other
Outfits
Other
Food and drinks
Total

## Guests
Guests
One line per guest or family. The answers, head counts and dietary needs add up on the Dashboard.
Name | Group | Answer | Adults | Kids | Dietary needs | Gift | Card sent | Thank you | Notes
Grandma Rosa and Grandpa Joe | Family | Yes | 2 | 0 |  |  |  |  | Bringing the photo album
Aunt Clara and Ben | Family | Yes | 2 | 2 | Vegetarian
Uncle Dan | Family | No | 1 | 0 |  | Book and card by post | x |  | Away that weekend
The Okafor family | School | Yes | 2 | 2
The Lindqvist family | School | Yes | 1 | 1 | Nut allergy |  |  |  | Ask about the cake
The Brandt family | School | Maybe | 2 | 1
The Varga family | School | Yes | 2 | 1
The Castell family | School | Yes | 1 | 2 | Gluten free
The Holloway family | School | No | 2 | 1 |  | Gift card
The Quill family | School |  | 2 | 1
The Rook family | School | Yes | 2 | 1
The Ashby family | School |  | 1 | 1
Nadia and Sam | Friends | Yes | 2 | 0 | Vegan
Iris | Friends | Yes | 1 | 0 |  |  |  |  | Can help with the games
Tomas and Ines | Friends | Maybe | 2 | 1
The Marlowe family | Neighbours | Yes | 2 | 2
Mr and Mrs Thorne | Neighbours |  | 2 | 0
Coach Wren | Other | Yes | 1 | 0 | Dairy free
The Fennimore family | School | Yes | 2 | 1
Jude | Friends |  | 1 | 0

## Tasks
Tasks
The checklist, counted back from the day of the party. Change the days before and the dates follow. 0 is the day itself, and a minus number is after it.
Task | Days before | Date | Who | Done | Status | Notes
Set the date, the time and the budget | 56 |  | Mum | x
Book the venue | 56 |  | Mum | x
Make the guest list | 49 |  | Mum and Dad | x
Send the invitations | 42 |  | Dad | x
Book the entertainment | 42 |  | Dad | x
Order the cake | 35 |  | Mum | x
Choose a theme and decorations | 35 |  | Mia and Mum | x
Plan the menu | 30 |  | Dad | x
Order the party bags | 35 |  | Mum
Book a face painter | 28 |  | Mum | x
Rent extra tables and chairs | 21 |  | Dad
Follow up on the answers | 21 |  | Mum
Plan the games and the music | 18 |  | Iris
Buy balloons and a banner | 14 |  | Dad
Confirm the entertainment | 14 |  | Dad
Make the plan for the day | 12 |  | Mum
Final guest count for the food | 10 |  | Mum
Shop for drinks and snacks | 7 |  | Dad
Confirm the venue and the cake | 7 |  | Mum
Ask helpers for a job each | 5 |  | Mum
Charge the camera and the speaker | 2 |  | Dad
Buy fresh food and ice | 1 |  | Dad
Pick up the cake | 1 |  | Mum
Set up the decorations | 0 |  | Everyone
Send thank-you notes | -3 |  | Mia and Mum
Return the rentals | -2 |  | Dad
Share the photos | -4 |  | Mum
Formulas:
Status = IF([Task]="","",IF([Done]<>"","Done",IF([Date]="","",IF([Date]<TODAY(),"Late",IF([Date]-TODAY()<=7,"This week","Coming")))))

## Food and drinks
Food and drinks
How much to buy, for everyone who may come: the yes, the maybe and those who have not answered. Amounts per person are for the whole party.
Adults |  |  | Extra, to be safe |  | 10% |  | A common rule for drinks: one per guest for each hour, and one more.
Kids | [6 empty] | Needed and packs round up, so there is always enough.
Item | Kind | Per adult | Per kid | Unit | Needed | Pack of | Packs | Price a pack | Cost | Bought | Where
Pizza | Food | 2 | 2 | slices |  | 8 |  | 11
Wraps and sandwiches | Food | 1 | 0.5 | pieces |  | 12 |  | 12
Crisps and snacks | Food | 0.5 | 0.5 | bags |  | 6 |  | 3.2 |  | x
Fruit platter | Food | 0.5 | 1 | portions |  | 12 |  | 10
Veggies and dip | Food | 0.3 | 0.2 | portions |  | 10 |  | 9.5
Soft drinks | Drinks | 2 | 1 | cans |  | 24 |  | 11 |  | x
Juice boxes | Drinks | 0 | 2 | boxes |  | 10 |  | 4.5 |  | x
Water | Drinks | 1 | 1 | bottles |  | 24 |  | 5
Coffee and tea | Drinks | 1 | 0 | cups |  | 40 |  | 7.5
Ice | Drinks | 0.05 | 0.05 | bags |  | 1 |  | 2.5
Plates | Supplies | 2 | 2 | plates |  | 50 |  | 4 |  | x
Cups | Supplies | 3 | 3 | cups |  | 50 |  | 3.5 |  | x
Napkins | Supplies | 3 | 3 | napkins |  | 100 |  | 2.5 |  | x
Total

## Budget
Budget
Everything you book or buy besides the food: what it costs, what you paid and when the rest is due.
Item | Category | Shop or vendor | Estimate | Final price | Paid | Still to pay | Pay by | Status | Notes
Community hall, 3 hours | Venue | Rowan Street hall | 180 | 180 | 50 |  | 2026-10-17
Unicorn cake, 24 slices | Cake | Corner bakery | 60 | 55 | 20 |  | 2026-10-23
Balloons and a banner | Decorations | Party shop | 45 | 38.6 | 38.6
Magician, 45 minutes | Entertainment | Magic Max | 150 | 150 | 0 |  | 2026-10-24
Face painting | Entertainment | Painted Faces | 90 | 90 | 20 |  | 2026-10-24
Extra tables and chairs | Rentals | Hire shop | 35 |  | 0 |  | 2026-10-22
Printed invitations | Invitations | Print shop | 18 | 16.5 | 16.5
Party bags | Favours |  | 40 |  | 0 |  | 2026-10-03
The final price counts once you know it. Until then the estimate does.
Formulas:
Status = IF([Item]="","",IF([Still to pay]<=0,"Paid",IF([Pay by]="","To pay",IF([Pay by]<TODAY(),"Late",IF([Pay by]-TODAY()<=7,"Due soon","To pay")))))

## The day
The day
The plan for the party itself, hour by hour, and who looks after what.
Time | What happens | Who | Notes
12:30 | Set up the room, balloons and tables | Dad and Iris
13:30 | Food and drinks out, music on | Dad
14:00 | Guests arrive, face painting starts | Mum
14:45 | Games in the hall | Iris
15:30 | Magician | Magic Max
16:15 | Pizza and snacks | Everyone
16:45 | Cake and singing | Mum
17:15 | Party bags and goodbyes | Mia
17:30 | Tidy up and return the hall key | Dad

## Start Here
Start here
Type only in the yellow cells. Everything else is calculated.
1 | Dashboard: the name of the party, the date, the time it starts and your budget.
2 | Guests: one line per guest or family, with their answer and how many adults and kids.
3 | Tasks: a checklist is ready, counted back from the date. Put an x under Done as you go.
4 | Food and drinks: how much each person eats or drinks, and the size and price of a pack. It says what to buy.
5 | Budget and The day: what you book or buy, what you paid, and the plan for the party hour by hour.
The example party, its guests and its shops are made up. Delete them and add your own.
Change the date and every task date moves with it.
Works in Google Sheets and Microsoft Excel, in any currency.