## Dashboard
Renovation dashboard
Everything here comes from the Budget, Costs and Timeline tabs.
Total budget | Committed | Paid | Still to pay | Contingency left | Budget committed | Left to spend
Room or area | Budget | Committed | Paid | Used | Status | Needs attention
[6 empty] | Next payments | To | Amount

## Budget
Budget by room
Type a budget for each room or area. Committed and paid come from the Costs tab.
Contingency | 10% | Money kept aside for surprises. Between 10 and 20% is usual.
Room or area | Budget | Committed | Paid | Still to pay | Left to commit | Used | Status
Kitchen | 18000
Bathroom | 9000
Living room | 4500
Primary bedroom | 3000
Whole house | 5000
Exterior | 3500
Total
Room budgets
Total budget
Contingency used
Contingency left
Costs with a room that is not on this list also count against the contingency.

## Costs
Quotes and costs
One line per quote, job or purchase. Quotes for the same job need the same job name.
Room | Job or item | Contractor or shop | Amount | Stage | Paid so far | Next payment due | Left to pay | Payment status | Quote check | Note
Kitchen | Cabinets and fitting | Oakline Kitchens | 7900 | Quote
Kitchen | Cabinets and fitting | Riverside Cabinet Co | 7200 | Hired | 2160 | 2026-10-10
Kitchen | Cabinets and fitting | HomeFit Kitchens | 8450 | Quote
Kitchen | Quartz countertops | Stone Works | 2650 | Bought | 2650
Kitchen | Appliances | Appliance store | 3100 | Bought | 3100
Kitchen | Kitchen electrics | Spark Electrical | 1450 | Hired | 0 | 2026-09-25
Bathroom | Bathroom remodel | Blue Tap Plumbing | 6800 | Hired | 2000 | 2026-10-18
Bathroom | Bathroom remodel | Clearwater Baths | 7450 | Quote
Bathroom | Tiles | Tile shop | 1380 | Bought | 1380
Bathroom | Vanity, toilet and shower | Bathroom store | 2150 | Bought | 1000 | 2026-10-04
Living room | Oak flooring | Floor Masters | 2900 | Hired | 0 | 2026-11-02
Living room | Painting | Fresh Coat Painters | 1100 | Quote
Living room | Painting | Local painter | 950 | Quote
Primary bedroom | Built-in closet | Riverside Cabinet Co | 2400 | Quote
Primary bedroom | Built-in closet | Closet Studio | 2150 | Quote
Whole house | Building permit | Building department | 450 | Bought | 450
Whole house | Dumpster rental | Waste hauler | 380 | Hired | 380
Whole house | Partial rewire | Spark Electrical | 3900 | Hired | 1950 | 2026-10-07
Exterior | Fence repair | Garden and Fence Co | 1250 | Quote
Exterior | Fence repair | Green Yard Services | 1480 | Quote

## Timeline
Timeline
One line per task. The coloured bars follow the start and end dates, one column per week.
Project start | 2026-08-31
Task | Room | Who | Start | End | Status
Demolition | Whole house | Us | 2026-09-04 | 2026-09-08 | Done
Partial rewire | Whole house | Spark Electrical | 2026-09-09 | 2026-09-18 | Done
Kitchen electrics | Kitchen | Spark Electrical | 2026-09-19 | 2026-09-23 | Done
Bathroom remodel | Bathroom | Blue Tap Plumbing | 2026-09-22 | 2026-10-10 | In progress
Cabinets and fitting | Kitchen | Riverside Cabinet Co | 2026-09-26 | 2026-10-07 | In progress
Drywall repair in the hall | Whole house | Handyman | 2026-09-24 | 2026-10-01 | Delayed
Quartz countertops | Kitchen | Stone Works | 2026-10-08 | 2026-10-14 | Planned
Oak flooring | Living room | Floor Masters | 2026-10-15 | 2026-10-22 | Planned
Painting | Living room | Not chosen yet | 2026-10-23 | 2026-10-30 | Planned
Built-in closet | Primary bedroom | Not chosen yet | 2026-11-02 | 2026-11-09 | Planned
Fence repair | Exterior | Not chosen yet | 2026-11-11 | 2026-11-14 | Planned
Final clean and punch list | Whole house | Us | 2026-11-17 | 2026-11-21 | Planned
Colours: | Done | In progress | Delayed | Planned | This week

## Start Here
Start here
Type only in the yellow cells. Everything else is calculated.
1 | Budget: list your rooms or areas with a budget for each, and set the contingency (10 to 20% is usual).
2 | Costs: add every quote, job and purchase. Quotes for the same job get the same job name.
3 | When you hire someone or buy something, change the stage from Quote to Hired or Bought.
4 | When you pay, update 'Paid so far' and the next payment date. Late payments turn red.
5 | Timeline: add each task with its start and end dates, and the bars fill in week by week.
6 | Dashboard: budget used per room, payments due soon, quotes to decide and the next task.
Only lines marked Hired or Bought count as committed. Quotes stay grey until you choose one.
The example rooms, quotes and tasks show how it works. Delete them and add your own.
Works in Google Sheets and Microsoft Excel, in any currency.